## Land Stewards
Short Term Priority | Short Term Priority | Short Term Priority | Short Term Priority | Action where PB is Lead | Action where PB is Coordinating Board | Timeframe | Notes | Status - As of Joint Meeting with Select Board on Jan 13, 2020 | Additional Status from PB | Possible Studies | Potential for Regulatory Changes / Bylaw Amendments

## Conservation Commission
Short Term Priority | Aspiration | Goal | Strategy | Action where PB is Lead | Action where PB is Coordinating Board | Timeframe | Notes | Status - As of Joint Meeting with Select Board on Jan 13, 2020 | Additional Status from PB | Possible Studies | Potential for Regulatory Changes / Bylaw Amendments | Potential for Regulatory Changes / Bylaw Amendments | Potential for Regulatory Changes / Bylaw Amendments | Potential for Regulatory Changes / Bylaw Amendments | Potential for Regulatory Changes / Bylaw Amendments | Potential for Regulatory Changes / Bylaw Amendments | Potential for Regulatory Changes / Bylaw Amendments | Potential for Regulatory Changes / Bylaw Amendments | Potential for Regulatory Changes / Bylaw Amendments

## Aspirations 1-3
Short term priority | Aspiriation | Goal | Strategy | Action | Lead Responsibility | Status from Lead Group | Status from Supporting Group
| Aspiration 1 - Maintain its rural character and celebrate its heritage | Goal 1.1 - Protect the towns heritage and character through the preservation of both natural and historic scenic areas, roadways and landscape features. | Strategy 1.1.1. Protect the town’s most important landscape features. | Action 1.1.1.1. Review and prioritize recommendations of Boxborough Reconnaissance Report: Freedom’s Way Landscape Inventory and implement as appropriate. | Historical Commission
|  |  |  | Action 1.1.1.2. Continue to review recommendations of the Massachusetts Audubon Society report Land Management Plans for Grasslands and Meadows on Town-Owned Land in Boxborough, Massachusetts. Implement recommendations as appropriate. | Conservation Commission | The Audubon report recommendations have being implemented and managed as follows: Flerra and Patch Hill are being managed as "Grasslands" by regular mowing after July 15th with the specific objective of providing habitat for ground nesting birds (i.e. bobolinks) at Flerra. Rolling Meadow, Beaver Brook Meadow, fields at Have Not Pond and a portion of Flagg Hill are being managed as "Meadow" by a once a year cut typically after October 1. Hager Meadow has been intermittently managed as pasture in an effort to diversify early successional habitat types. Continuing as ongoing activity. The Audubon report recommendations have been implemented and managed as follows: Flerra and Patch Hill are being manged as "Grasslands" by regular mowing after July 15th with the specific objective of providing habitat for ground nesting birds (i.e. bobolinks) at Flerra. Rolling Meadow, Beaver Brook Meadow, fields at Have Not Pond and a portion of Flagg Hill are being managed as "Meadow" by a once a year cut typically after October 1. Hager Meadow has been intermittently managed as pasture in an effort to diversify early successional habitat types.
|  |  |  | Action 1.1.1.3. Provide input to the ongoing evolution of the Steele Farm Management Plan. | Steele Farm Management Advisory Committee
|  |  |  | Action 1.1.1.4. Conduct a survey and inventory of historic resources. | Historical Commission
|  |  |  | Action 1.1.1.5. Consider additional protections for local historic resources in consultation with the Massachusetts Historical Commission. | Historical Commission
|  |  | Strategy 1.1.2. Preserve and reinforce the Town Center District as Boxborough’s center for governance, municipal services, and town-wide events. | Action 1.1.2.1. Review existing Town Center zoning and design guidelines, making necessary amendments to preserve character and encourage appropriately scaled and designed developments. | Planning Board
|  |  |  | Action 1.1.2.2. Create signage (e.g.,“Welcome to Boxborough”) in Town Center District to enhance town image and visibility as well as to improve ease of navigation. | Historical Commission
|  |  | Strategy 1.1.3. Promote the town’s natural, recreational, and historical assets. | Action 1.1.3.1. Develop a heritage/scenic guide to generate awareness and promote community assets, events, programs, and resources to local residents and regional visitors. | Recreation Commission | We are the lead on this and are supposed to work with the Historical Commission, but given the lack of Town Hall staffing support for the Recreation Commission, we feel that we can no longer support this initiative alone.
|  |  |  | Action 1.1.3.2. Explore opportunities to hold seasonal walking tours for local trails and historical points of interest. | Land Stewards | Action 1.1.3.2. Explore opportunities to hold seasonal walking tours for local trails and historical points of interest. Lead responsibility: LS Coordinate with: RC, WBC, SFAC, HC Timeframe: Resources: Volunteers --in FY19 conducted 4 themed walks, coordinating with Historical Commission, Well-Being Committee, Steele Farm Advisory Committee, Boxborough Birders, Blanchard PTF. --conducted one walk so far in FY20 and plan to continue
|  |  |  | Action 1.1.3.3. Update the Town of Boxborough Open Space and Recreation Plan before expiration of the 2015-2022 plan. | Town Planner
|  |  | Strategy 1.1.4. Proactively plan for water resource management and protection. | Action 1.1.4.1. Reinstate Water Resources Committee. | Select Board, Board of Health | A Water Resources Working Group drafted a new WRC charter. BSB authorized the WRC on October 29, 2018 and began making appointments. At-large members (voting and non-voting) and the Fin. Com. designee have yet to be appointed.
|  |  |  | Action 1.1.4.2. Plan for long-term water supply and wastewater management to support private and municipal goals. | Water Resources Committee | WRC reviewed previous planning completed by the town, ownership and status of the test well sites, water quality issues, and regulatory requirements. It is creating a GIS of the town's water resources with funding from the MAPC Technical Assistance Program, and Town Meeting approved funding to monitor groundwater resources. See Actions 1.3.1.1 and 3.1.2.1. Substantial progress. WRC continued its planning for a municipal water system to address water and wastewater issues in the western part of town (see Action 3.1.2.1. below). It is currently seeking funding sources. It submitted a proposal under ARPA to design water mains in Boxborough to serve this area and is working with the Littleton Water Department and property owners for the other infrastructure that would be needed. It has coordinated with the Boxborough Sustainability Committee and Town Planner regarding a possible MVP Action Grant. It also coordinated the town's response to PFAS contamination, coordinated the assesment by RCAP Solutions of water quality in private wells, and helped to install three wells for monitoring groundwater levels. (See Action 3.1.2.1.) The WRC plans to pursue other sources of funding, as well. The town has approved a small amount of money for certain phases of this work and has covered legal cost for town counsel. Otherwise, the WRC has no funding to pursue this.
|  |  |  | Action 1.1.4.3. Review Watershed and Aquifer Protection zoning to protect Zone IIs and existing and potential well sites in Boxborough and neighboring towns. | Water Resources Committee, Board of Health, Planning Board | Status: 1) The Town Planner is working with an outside consultant to update stormwater bylaw to align with the latest requirements of the MS 4 permit (EPA NPDES Permit). The Planning Board will review and provide comments on the proposed stormwater bylaw in anticipation of presentation at Annual Town Meeting in May 2020. 2) Water Resource Committee has received a grant for an educational tool and analysis tool regarding the Town’s water sources, availability, and quality. The Planning Board will work with the Water Resource Committee to review the data and to make this data available to the public for future planning purposes. 3) UMass students have digitized the 1978/1981 maps of the aquifer protection overlay district (APOD) and provided data files to the town. Hoping to incorporate those files into the town’s GIS system. Considering options for updating the 1978/1981 aquifer protection district mapping but may require funding. | WRC reviewed Zone IIs and well sites in Boxborough and neighboring towns, and the state regulatory requirements, but has not addressed the zoning bylaw. Behind schedule. Having three boards with joint lead responsibility may be holding up progress on this Action. One approach would be for the WRC and BoH to provide recommendation to the PB and have the PB incorate them into zoing audits and/or amendments.
|  | Goal 1.2. New development and redevelopment will be physically designed to blend into the town’s rural landscape. | Strategy 1.2.1. Strengthen the design review process for any development without hindering economic development. | Action 1.2.1.1. Review existing design guidelines for Town Center District and update guidelines to include considerations for larger scale developments in other commercial areas. | Design Review Board | The Design Review Board is in the process of updating a new draft of the Design Review Board Design Guidelines to accommodate this action item.
|  |  |  | Action 1.2.1.2. Adopt and incorporate updated building design guidelines into the review process to ensure future developments are physically consistent with town character. | Design Review Board | The Design Review Board is in the process of updating a new draft of the Design Review Board Design Guidelines to accommodate this action item.
|  | Goal 1.3. Protect and/or acquire additional lands for conservation, water resource protection, wildlife habitat, agricultural land preservation, recreation, trails, and wildlife corridors. | Strategy 1.3.1. Proactively review and amend the list of existing and desired parcels of land for acquisition and preservation. | Action 1.3.1.1. Continue to review and prioritize acquisition of lands that protect multiple resources and assets. | Planning Board |  | WRC reviewed the status of the previous test well sites, one new site, and worked with the Town Administrator in discussing them with several of the landowners and abutters.
|  |  |  | Action 1.3.1.2. Periodically review land classified under MGL Chapters 61, 61A, and 61B and be prepared to make appropriate recommendations, including exercising Town’s right of first refusal. | Planning Board |  | No action to date by the WRC.
|  |  |  | Action 1.3.1.3. When acquisition may not be feasible, work with private landowners, investors, and conservation groups to place appropriate conservation easements or agricultural restrictions on their land to ensure it remains undeveloped in perpetuity | Conservation Commission, Agricultural Commission | The AC worked with the Boxborough Conservation Trust, Town Administrator, and BSB to clarify the authority of Agricultural Commissions under 2016 amendments to Massachusetts law, e.g. Agricultural Commissions may now hold land. The AC entered into a MOA with the Con. Com. and BSB to assume oversight of the agricultural parcel under the conservation restriction on Paddock Estates. On-going. The Commission continues to work closely with the Boxborough Conservation Trust (BCT) to identify land conservation oppertunities other than acquisition. Over the last 4 years the Commission accepted new Conservation Restructions for Inches Woods (approx. 25 acres) and Elizabeth Brook Knoll (approx. 15 acres). Other opportunities continue to be identified and vetted on an as needed basis. | The Commission continues to work closely with the Boxborough Conservation Trust (BCT) to identify land conservation opportunities other than acquisition. Over the last 2 years the Commission accepted new Conservation Restrictions for Inches Woods (approx. 25 acres) and Elizabeth Brook Knoll (approx. 15 acres). Other opportunities continue to be identified and vetted on an as needed basis.
|  |  |  | Action 1.3.1.5. Include a line item in the Town Meeting Warrant each year for the Town’s Conservation Trust Fund, to provide funding for land acquisition. | Conservation Commission | A $10,000 warrant article request to fund the Conservation Trust Fund (CTF) was prepared, presented and passed at the 2019 ATM marking the 9th consecutive year of approved funding for the CTF. CPA has been the source of funding for the CTF since ATM 2017. A $10,000 warrant article request to fund the Conservation Trust Fund (CTF) was prepared, presented and passed at the 2021 ATM marking the 11th consecutive year of approved funding for the CTF. CPA has been the source of funding for the CTF since ATM 2017
|  |  |  | Action 1.3.1.6. Consider long-term bonds using Community Preservation Funds for land acquisition. | Finance Committee
| Aspiration 2. Is engaged and welcoming | Goal 2.1. Support diversity by valuing, respecting, appreciating, and welcoming individuals – those who reside, visit, work, or pass through Boxborough – of all ages, genders, socioeconomic levels, cultural heritages, racial/ethnic backgrounds, sexual orientations, gender identities, religions, and ability levels. | Strategy 2.1.1. Offer diversity and anti-bias training to the community. | Action 2.1.1.1. Continue and expand anti-bias and diversity training for all Boxborough employees. | Select Board
|  |  |  | Action 2.1.1.2. Offer free diversity and anti-bias workshops for the community. | Community Services Coordinator
|  |  | Strategy 2.1.2. Explore the needs of the Boxborough community as they relate to diversity. | Action 2.1.2.1. Apply for a Community Health Needs Assessment grant and work to implement recommendations as they relate to diversity. | Community Services Coordinator
|  | Goal 2.2. Increase resident participation in town-wide events, programs, and government. | Strategy 2.2.1. Work with community organizations and networks to encourage public participation in town events and utilization of community assets. | Action 2.2.1.1. Continue leveraging private resources by collaborating with local businesses, nonprofit organizations, and community networks in promoting townwide festivals such as Fifer’s Day, WinterFest, and the Harvest Fair, as well as community service activities such as the Adopt-a-Highway program. | Public Celebrations & Ceremoneis Committee |  | The COA promotes town activities through notifications (email, newsletter, etc) as well as by participating in appropriate events (e.g., info table at Fifers' Day)
|  |  |  | Action 2.2.1.2. Encourage one or more local organizations to sponsor and hold welcoming events for newcomers. | Public Celebrations & Ceremoneis Committee
|  |  |  | Action 2.2.1.3. Continue using local venues such as the Sargent Memorial Library and annual events such as Fifer’s Day, WinterFest, and the Harvest Fair as opportunities to convey a welcoming atmosphere in town and an “open door policy” with municipal officials. | Library Board of Trustees, Public Celebrations & Ceremoneis Committee
|  |  |  | Action 2.2.1.4. Explore establishment of (a) new community garden(s). | Agricultural Commission | The AC discussed this with the former owners of Paddock Estates. They appeared interested, but other issues came up, including sale of the property. We explored a possible community garden near the condominiums west of Rt. 495.
|  | Goal 2.3. Increase resident participation in Town government. | Strategy 2.3.1. Communicate activities and policies widely, with the intention of reaching all households. | Action 2.3.1.1. Develop a town-wide communication and outreach plan. | Select Board
|  |  |  | Action 2.3.1.2. Provide a periodical e-newsletter on Town government activities, issues, and decisions; encourage residents to sign up on the Town’s website. | Select Board
|  |  |  | Action 2.3.1.3. Explore options for Internet-based resident engagement platforms. | Select Board
|  |  |  | Action 2.3.1.4. Consider having a language translation and interpretation firm on retainer for important Town publications and events. | Select Board
|  |  |  | Action 2.3.1.5. Expand networks and cultivate new relationships with cultural and faith-based organizations to encourage participation in Town governance that reflects the town’s growing diversity | Select Board
|  |  | Strategy 2.3.2. Cultivate new members for Town boards and committees. | Action 2.3.2.1. Periodically hold informal meetings between Town board/ committee members and residents to exchange ideas and information. | Select Board
|  |  |  | Action 2.3.2.2. Reach out to new Boxborough residents with students enrolled in the Acton-Boxborough School District to welcome them to town and provide information. | Select Board
|  |  |  | Action 2.3.2.3. Establish and maintain a citizen skills bank or volunteer database as a resource to Town boards and committees. | Town Administrator, Select Board
|  |  |  | Action 2.3.2.4. Include information on Town boards and committee openings, roles and responsibilities, and opportunities to get involved at Town events and prominently on the Town’s website. | Select Board
| Aspiration 3. Is thoughtfully developed: | Goal 3.1. Guide and concentrate commercial growth in Business, Office Park, and Town Center districts. | Strategy 3.1.1. Create a long-term vision for the town’s commercial areas, prioritizing enhanced quality of life over expanding the commercial tax base. | Action 3.1.1.1. Create and designate an Economic Development Committee (EDC) or similar committee. | Select Board | Completed UMASS Economic Development Study which provided a baseline assessment of current conditions, surveyed residents on interests, and outlined development sscenarios with recommendations on next steps. (December 2020)
|  |  |  | Action 3.1.1.2. Develop a 10-15 year Economic Development Plan under the guidance of the EDC. | Economic Development Committee | Will be developed with output from UMASS Study that completes in Aug ‘20. Next steps would include developing Economc Development Plan (EDP) based on results of UMASS Study and other insights based on current environment, and to conduct "public hearing" listening sessions on the EDP with residents and other boards/committees prior to adoption by the EDC.
|  |  |  | Action 3.1.1.3. Index commercial development opportunity sites for potential private acquisition, assembly, or development. | Economic Development Committee | Focus continues on Town Center and adjacent Town Center property for Multi-Use, Village Style, Small Scale Commercial, Civic & Cultural Adams Place / Beaver Brook remains opportunity for Multi-Use/Commercial Development Results of UMASS Study, Water Resources, etc. will guide specific plans. Complete. Commercial development sites have been identified, and discussion has taken place with specific land owners. Town Center land is available for Town acquition - oppertunity for cooperative development. Adams Place - Gutierrez Property - potential for commercial/light industrial development. 1414 Lincoln Properties - future development unknown (awaiting for closure on Vibalogics and Arranta Bio). Beaver Brook - Campanelli acquired property - development plans being developed.
|  |  |  | Action 3.1.1.4. Conduct a thorough market analysis to identify local and regional retail market opportunities. | Economic Development Committee | Market analysis included in scope of UMASS Study that completes in Aug ‘20. Market analysis was completed as part of the UMASS Study (Dec. 20).
|  |  | Strategy 3.1.2. Continue to assess the need for and feasibility of implementing public water supply in key areas. | Action 3.1.2.1. Identify priority areas for receiving a public water supply based on need and feasibility. | Water Resources Committee | WRC is working with DEP, MassDOT, Town Administrator, Town Counsel, and affected property owners to resolve water supply issues identified by DEP in the western part of town. See Action 3.1.5.1. Substantially complete. The WRC identified the area west of I-495 as the highest priority for a public water system, based on the state's concerns about this area and the proximity of water sources. It is also evaluating a larger service area, but will need data from the first phase of the project (see Action 1.1.4.2.)
|  |  | Strategy 3.1.3. Establish a village business district as Boxborough’s commercial center. | Action 3.1.3.1. Explore development of an area for a village business district and obtain property owner buy-in, if necessary. | Economic Development Committee | Specific locations to be identified as part of UMASS Study Discussions have occurred and will continue with key land owners (Cisco, Lincoln Properties, Gutierrez, Town Center LLC) Met with land owners of potential "village districts" (Adams Place, 1414 Mass. Ave., Cisco/Campanelli, and Town Center LLC). Only viable location identified is the current Town Center district: Adams Place - current land owner (Guiterrez) does not intend to develop a village center due to proximity to wetlands and market conditions, and intend a 150,000 sq. foot commercial/industrial type buildign, but open to working with the town; 1414 Mass. Ave. - Lincoln Properties focus is on Arranta Bio and Vibalgics buildout, with no stated plans for village style development. Remaining Town Center land along Mass. Ave. and at crossroad of Mass. Ave. and Stow Road available for acquition from land owners. This is the ideal (and currently zoned) location for a "Rural Village Center", which was identified as a preferred vision coming out of the UMASS Study - EDC will continue to pursue oppertunities for development.
|  |  |  | Action 3.1.3.2. Investigate potential zoning amendments to encourage and support appropriate development and utility support in a village business setting. | Economic Development Committee | Short term zoning opportunities (Parking, Agricultural Business, Cafe/Bakery, Small Restaurant) based on desires identified in Phase 1 of the UMASS Study Longer-term opportunities to address other specified land areas and desired businesses (Office Park). Zoning change adopted at 2019 Annual Town Meeting - Specialty Food Shops, Parking Requirements adjusted. Future - Review Town Center/ "Main Street" zoning in partnership with land use committees and make recommendations; Partner with Campanelli on future of Beaver Brook Park (aka Cisco).
|  |  |  | Action 3.1.3.3. Recruit appropriate businesses to the village business district through marketing efforts or financial incentives such as relocation tax credits. | Economic Development Committee | Marketing efforts pending clarity on Town vision for development. Action ties in with Action 3.1.3.2.
|  |  | Strategy 3.1.4. Implement land use policies that support and encourage appropriately scaled and mixed-use developments in key areas of town. | Action 3.1.4.1. Conduct a thorough review of the Town’s land use controls, including dimensional requirements and conservation bylaws on commercially zoned land, to identify barriers to growth for appropriately scaled development. | Planning Board | Status: 1) The Planning Board is working with the EDC and the UMass Study (Phases 1 and 2) to assess opportunities for changes to dimensional requirements and other potential zoning changes to address barriers to growth for appropriately scaled development. Phase 1 study has been completed. 2) The Planning Board has received approval from Town Meeting for $10,000 for a zoning bylaw audit. The zoning bylaw audit will be an initial step in cleaning up the zoning bylaws for inconsistencies and omissions and positioning the bylaws more easily for future amendments.
|  |  |  | Action 3.1.4.2. Consider regulatory tools that can guide and encourage growth in appropriate areas, such as incentive zoning overlays or floor area ratio (FAR) density bonuses for developments that incorporate affordable housing, or agricultural or open space management. | Economic Development Committee | Further research required leveraging results of UMASS Study and Zoning Audit. Assess and recommend opportunities based on areas of development interest.
|  |  | Strategy 3.1.5. Catalyze private investment in key commercial districts. | Action 3.1.5.1. Invest in public infrastructure in commercial areas to attract private development. | Economic Development Committee | Requires further study and insight from Water Resources, BoH, PB, Fin Comm & Select Board. Sidewalk construction from Liberty Square Road to Library provides pedestrian infastructure supporting and promoting village style development. EDC recommeds use of Sidewalk and other funds for expansion of sidewalk infastructure along Mass. Ave. and Stow/Middle Road to tie Boxborough's Town Center, Business District and municipal resources together. Requires further study and insight from Water Resources, BoH, PB, FinComm, and Select Board. | WRC is evaluating this for the western [art of town as part of Action 3.1.1.1. The timeframe is not realistic for investing in water infrastructure.
|  |  |  | Action 3.1.5.2. Engage in publicprivate partnerships to stimulate appropriate forms of development and redevelopment on key opportunity sites. | Economic Development Committee | Requires clarity on town vision for development Discussions have occurred and will continue with key land owners (Cisco, Lincoln Properties, Gutierrez, Town Center LLC) Potential oppertunities at Town Center and Office Park Districts.
|  |  |  | Action 3.1.5.3. Consider financial incentives to encourage property improvements, local hiring, or capital improvements through reduced tax rates, abatements, or small grants. | Economic Development Committee | Requires clarity on town vision for development and priorities Initial research indicates opportunities for Local Incentives
|  | Goal 3.2. Attract and retain businesses in key existing and emerging industries. | Strategy 3.2.1. Promote Boxborough as a great place to do business for existing and prospective businesses. | Action 3.2.1.1. Develop and implement a marketing strategy plan to attract appropriate types of development or businesses to the town’s commercial districts. | Economic Development Committee | Requires clarity on town vision for development before marketing efforts can begin. Leverage Town's location, current economic environment and MassEcon membership to highlight Boxborough. Support Economic Development oppertunities in "ombudsman" type role.
|  |  |  | Action 3.2.1.2. Engage in partnerships with area chambers of commerce or merchants associations. | Economic Development Committee | Held successful 1st Business Breakfast in Boxborough in October 2019 Board engagement with local groups (Boxborough Businesses, West Acton Business Association). Exploring opportunities to engage with MetroWest Chamber of Commerce as well as potential establishment of Boxborough Business Chamber. Membership in MassEcon to gain access to state develoipment organizations, developers and other development resouces.
|  |  |  | Action 3.2.1.3. Identify target industries to market development incentives and land use policies to attract and retain businesses in those industries. | Economic Development Committee | Requires clarity on town vision for development UMASS Study will inform market based opportunities given land/infrastructure constraints/opportunities. Leverage Town's location, current economic environment and MassEcon membership to highlight Boxborough. Identify target oppertunities to secure and support business. | WRC has provided input to EDC as needed.
|  |  |  | Action 3.2.1.4. Consider financial incentives to attract small businesses, such as establishing revolving loan funds or implementing relocation tax credits. | Economic Development Committee | Requires clarity on town vision for development and priorities Will be advised through UMass Study. Community Block Grant - Microenterprise Loan Program are complete. ARPA Funds request for Small Business in response to impacts from COVID-19. Other insentive programs to be pursued for target oppertunities.
|  |  | Strategy 3.2.2. Foster Boxborough’s participation in a sustainable regional agricultural economy. | Action 3.2.2.1. Develop a community food plan to create a vision, identify issues, barriers, challenges, and opportunities in the agricultural economy. | Agricultural Commission | No action to date.
|  |  |  | Action 3.2.2.2. Ensure that Town policies and regulations are supportive of agriculture. | Agricultural Commission | The Commission coordinated with the Con. Com., BSB, Town Planner, Building Inspector, BoH, and Mass. Farm Bureau to clarify regulatory requirements and exemptions for agriculture. It advocated for earlier involvement in issues that involve agriculture. See Actions 3.2.2.6 and 3.2.2.7 for specific policies and regulations.
|  |  |  | Action 3.2.2.3. Recruit existing loca farmers and work with non-profit organizations to cultivate workforce development, training, and educational programs | Agricultural Commission | No action to date.
|  |  |  | Action 3.2.2.4. Expand land lease programs for local farms and farmers using town-owned lands to increase agricultural viability. | Agricultural Commission | The Commission is finalizing a license agreement for a parcel of town conservation land. It reviewed the policies of other towns, evaluated possible sites with the Con. Com., and prepared a draft license agreement for review by the Town Administrator and Town Counsel. It will use this as a template for other agreements in the future.
|  |  |  | Action 3.2.2.5. Periodically review the Boxborough Right to Farm Bylaw and make amendments as necessary. | Agricultural Commission | The Commission reviewed this periodically, particularly an amendment requiring realtors to notify prospective buyers of the Bylaw (the provision that was stricken before Town Meeting passed the Bylaw). It recommended no further action at this time.
|  |  |  | Action 3.2.2.6. Review Town policies and regulations and amend as necessary to ensure clarity and consistency of agricultural use definitions. | Agricultural Commission | The Commission has not yet identified any inconsistencies in need of formal amendment.
|  |  |  | Action 3.2.2.7. Consider adding “Agricultural Business” in the Zoning Bylaw’s Use Regulations as a permitted use in residential and business districts to allow farm stands and similar agricultural business operations at existing and future farms. | Agricultural Commission | Commission reviewed this with the Town Planner in 2016 and drafted a memo for his review.
|  |  | Strategy 3.2.3. Preserve farmland and areas with soils favorable for agriculture. | Action 3.2.3.1. Identify and index opportunity sites for farmland preservation in accordance with the 2015-2022 Open Space and Recreation Plan. | Agricultural Commission | The AC evaluated two sites in the Open Space and Recreation Plan that were either for sale or on the tax title list. It found that one was not suitable for farmland, and one required further evaluation for forestry potential. An "Ongoing" timeframe for this Action may be more appropriate.
|  |  |  | Action 3.2.3.2. Identify federal and state incentives or supplemental revenue streams to support viability for working farms. | Agricultural Commission | Incomplete.
|  |  |  | Action 3.2.3.3. Consider using CPA funds to acquire and preserve farmlands, giving priority to properties under Chapter 61A and 61B. | Agricultural Commission | The Commission has a representative on the CPC who can advocate using CPA funds for agricultural land, as needed.
|  | Goal 3.3. Create a positive business environment and seek to attract businesses that would enhance the quality of life for Boxborough residents. | Strategy 3.3.1. Build municipal capacity to improve local business environment. | Action 3.3.1.1. Review current permitting regulations and make necessary amendments to improve consistency in fees and enforcement. | Building Department
|  |  |  | Action 3.3.1.2. Develop a guide for permitting or doing business in Boxborough to streamline business regulatory processes and promote transparency | Economic Development Committee | Action item in process with target of a framework and guide to be developed in 2022. Streamlining process / transparency will require training and change in culture with respect to businesses.
|  |  |  | Action 3.3.1.3. Proactively meet with local businesses to understand needs for space and employee amenities. | Economic Development Committee | EDC informal meetings with different local businesses First Boxborough Business Breakfast held in October 2019 Meetings held and planned with key business and property owners (Cisco, Lincoln Properties, Gutierrez, Town Center LLC)
|  | Goal 3.4. Local regulations will reflect community aspirations and yield desired results. | Strategy 3.4.1. Minimize development impact by protecting town’s limited water supply and managing stormwater runoff. | Action 3.4.1.1. Review areas where stormwater runoff issues exist due to concentration of impervious surface. | Conservation Commission | The Commission ensures conformance with best practices for stormwater management in cases of new development or redevelopment when owners and/or applicants file a Notice of Intent under the Wetlands Protection Act and/or Town Wetlands By-Law. Existing non-conforming and/or problematic runoffs locations are typically unknown until identified by a wetlands filing. The Commission has very limited ability to address existing non-conforming conditions unless prompted by new and/or proposed activity. Limited activity, as-needed. The Stormwater Bylaw approved in 2020 places the responsibility and authority for regulating stormwater runoff primary the Select Board. The Conservation Commission ensurres conformance with the best practices for stormwater management only in cases of new development or redevelopment when owmers and/or applicants file a Notice of Intent under the Wetlands Protection Act and/or Town Wetlands By-Law. Exisiting non-conforming and/or problematic runoffs locations are typically unknown until idnetified by a wetlands filing. The Commission has a very limited ability to address exising non-conforming conditons unless prompted by new and/or proposed activity. | WRC is addressing road salt in stormwater runoff under Action 3.1.2.1. WRC coordinates with the TP on the MS4 stormwater permit.
|  |  |  | Action 3.4.1.2. Incorporate lowimpact design guidelines into the development review process. | Planning Board | Status: 1) Mr. Corson is working with an outside consultant to update the stormwater bylaw to align with the latest requirements of the MS 4 permit (EPA NPDES Permit). The Planning Board will review and provide comments on the proposed stormwater bylaw in anticipation of presentation at Annual Town Meeting in May 2020. 2) The Planning Board will continue to identify and encourage opportunities for reduced water consumption in new development projects such as rainwater collection and reduced irrigation where feasible.
|  |  |  | Action 3.4.1.3. Revisit subdivision regulations regarding roadway widths and amend as appropriate. | Planning Board | Status: 1) The Planning Board noted that the roadway regulations in the Subdivision Regulations relate to traffic and public safety needs and any modification of roadway widths need to be discussed with public safety officials. 2) The Planning Board will further investigate the use of more pervious roadway materials with town staff, including the DPW and the town’s consulting engineer, noting that such discussion will need to address impacts to snow plowing. 3) Per the Town Planner, the Town has applied for a Municipal Vulnerability Preparedness (MVP) Grant from the Governor’s Office which can encompass many environmental needs relating to storm water and roadway width and material requirements. The MVP grant program provides support for cities and towns in Massachusetts to begin the process of planning for climate change resiliency and implementing priority projects. The state awards communities with funding to complete vulnerability assessments and develop action-oriented resiliency plans. Communities who complete the MVP program become certified as an MVP community and are eligible for MVP Action grant funding and other opportunities. If the grant is received, the Planning Board will work with the Town Planner to implement resiliency plans.
|  |  | Strategy 3.4.2. The development review process will look to limit traffic and air quality impacts of new development. | Action 3.4.2.1. Consider hiring a consultant with air quality impacts/public health experts to determine appropriate expectations for new development. | Town Planner
|  |  |  | Action 3.4.2.2. Determine the scale of development that would require additional traffic impact analysis and incorporate guidelines into the development review process. | Town Planner
|  |  | Strategy 3.4.3. New housing and commercial development will prioritize design quality, energy efficiency, and preservation of open space. | Action 3.4.3.1. Explore the potential use of regulatory tools such as transfer of development rights (TDR), natural resource protection zoning, or payment-in-lieu-of-taxes (PILOT) programs to support open space preservation and affordable housing development in the Town’s Agricultural-Residential Zoning District. | Planning Board
|  |  |  | Action 3.4.3.2. Provide floor area ratio (FAR) density bonuses for commercial and housing development that incorporate active agricultural management or open space preservation in their overall development design. | Planning Board
|  |  |  | Action 3.4.3.3. Modify the Building Code as necessary to require excellence in energy efficiency for commercial and residential development, considering incorporation of the Massachusetts Stretch Energy Code and Leadership in Energy and Environmental Design (LEED) green building standards into the code. | Sustainability Committee | Two members of the Sustainability Committee met with the Boxborough Building Commissioner on 10/26/18 to discuss the current building code and potential for Boxborough’s adoption of the state’s “Stretch Code”. Based on information gathered at this meeting and through subsequent research, the SC recommends the Town formally adopt the Massachusetts “Stretch Energy Code” as updated by the Board of Building Regulations and Standards (BBRS) and the Department of Energy Resources (DOER) in 2017. The updated Stretch Code has been simplified, is more in line with the base code and is more stringent than the previous 2015 version. A significant benefit is that new homes can be designed to meet energy efficiency standards based on performance rather than prescriptive standards allowing builders more flexibility in achieving the standards. Energy savings from meeting these standards are known to generate cost savings early in the building’s lifespan. As of November, 2019, 278 municipalities out of 351 in the Commonwealth have adopted the Stretch Code. A map of these communities and a summary of the updated Stretch Code is below.
|  |  |  | Action 3.4.3.4. Consider proposing requirements for larger developments to include at least one passive building (with net-zero energy consumption) in new construction, retrofit, or redevelopment plans. | Sustainability Committee | The Sustainability Committee needs to study this goal further and decide whether or not to propose a bylaw to that effect.

## Aspirations 4-7
Short term priority | Aspiriation | Goal | Strategy | Action | Lead Responsibility | Status from Lead Group | Status from Supporting Group/ Additional updates
| Aspiration 4. Provides high quality services and amenities | Goal 4.1. Ensure conservation and recreation attractions are well maintained, safe, and easy to access. | Strategy 4.1.1. Maintain and enhance trail networks. | Action 4.1.1.1. Maintain trail markers, kiosks, and boardwalks. | Land Stewards | Action 4.1.1.1. Maintain trail markers, kiosks, and boardwalks. Lead responsibility: LS Coordinate with: ConsCom, DPW --taking advantage of grant money from the Bettering Boxborough Together CHNA-15 grant, purchased 4 large kiosks for Wolf Swamp, the library/Hager trails, Cisco/Beaverbrook property (at Fifer’s Field) and at Liberty Field (Patch Hill trails) | A variety of activity remains on-going. Removal of fallen trees from the trails is on-going. The next "work party" is scheduled for 11/14/2020 with a focus on fallen tree removal work. A successful grant application has provided for the furnishing of 3 new kiosks at trailheads (at Wolf Swamp, Fifer's Field, and Hager Land). The Stewards led the successful pursuit of grant and CPA funds to provide for the reconstruction of the Hager Bridge (to be completed in 2021). Additional on-going activity includes: Coordination with volunteer groups (e.g. students, 80-90 Central Street) to perform maintenance work. Coordination with the DPW for additional labor when needed. Communication and coordination of Steward activity via a Facebook page. Replacement of trail markers. Conservation Commission has a variety of activity that remains ongoing: the Stewards led the successful pursuit of grant and CPA funds to provide for the reconstruction of the Hager Bridge (to be completed later in 2021). Additional on-going activity includes: Removal of fallen trees form the trials in on-going. Coordination with volunteer groups (e.g. students, 80-90 Central Street) to perform maintenance work. Coordination and coordination of Steward activity via a Facebook page. Replacement of trail markers.
|  |  | Strategy 4.1.2. Ensure ease of access to conservation properties. | Action 4.1.2.1. Assess the need for additional off-street parking at conservation properties. | Conservation Commission | Action 4.1.2.1. Assess the need for additional off-street parking at conservation properties. Lead responsibility: ConsCom Coordinate with: RC, DPW, TP The need for additional parking has been identified along Littlefield Road for access to the Fort Pond Brook parcel. The next step toward implementation is to evaluate feasibility and cost of constructing a parking area in coordination with the DPW. A related enhancement will be to improve the communication (mapping) of parking locations on the maps at the kiosks (overlapping with activity under Action 4.1.1.1). The existing parking at other parcels has been evaluated and is considered to be adequate. In progress. The need for additional off-street parking has been identified along littlefield Road for access to the Fort Pond Brook parcel at a current trailhead location. The feasibility of constructiing a parking area has been confirmed in coordination with the DPW and the work has been started. The next step is applying for permission for Stonewal Removal (along a scenic road) with the Planning Board. A related enhancement will be to improve the communication (mapping) of parking locations on the maps at the kiosks (overlapping with activity under Action 4.1.1.1.). The existing parking at other parcels has been evaluated and is considered to be adaquate.
|  |  |  | Action 4.1.2.2. Assess the need for bicycle parking at trailheads and other conservation properties. | Conservation Commission | Action 4.1.2.2. Assess the need for bicycle parking at trailheads and other conservation properties. Lead responsibility: ConsCom Coordinate with: RC, LS, DPW, TP The need for bicycle parking was identified at Flerra Meadows, and a bicycle rack has been installed at Flerra through the efforts of the Recreation Commission involving grant funding to furnish the rack. Assessment of needs at other parcels has concluded that no additional bicycle parking is needed.
|  | Goal 4.2. Maintain excellent municipal facilities and services. | Strategy 4.2.1. Regularly review Town’s capital improvements needs and continue to plan for maintenance, in concert with the Town’s annual capital plan and Town Meeting. | Action 4.2.1.1. Continue to explore the creation of or finding locations for new Police and Fire Department facilities and Department of Public Works facilities. | Select Board | There is an active Building Committee for this action item. | Planning Board will audit Building Committee meetings. The COA Board Chair is a member of the Building Committee.
|  |  |  | Action 4.2.1.2. Explore regionalization or sharing of key pieces of equipment which the Town needs on a part-time basis. | Select Board | The most recent action for this item came in the form of the Veteran’s Affairs Officer. This is also an ongoing item.
|  | Goal 4.3. Enhance the quality and variety of recreation programs and facilities to meet current and future demand among all age groups and levels of ability. | Strategy 4.3.1. Address known recreational needs by upgrading or developing new facilities when feasible. | Action 4.3.1.1. Investigate options for the creation of a public swimming facility. | Recreation Commission | Action 4.3.1.1- Likely unable to complete until the town has public water. Also, no space in town to put it and concerns about liability issues.
|  |  |  | Action 4.3.1.2. Investigate the feasibility of developing tennis and basketball courts at Liberty Fields and Fifer’s Field. | Recreation Commission | Action 4.3.1.2- We have worked with Places and Associates, Inc. to develop a master plan for capital improvements to Liberty Field, including basketball and tennis courts. Fifer's Field is not a large enough space. We have worked with Places Associates, Inc. to develop a master plan for capital improvements to Liberty Field, including backetball and tennis courts which were approved at the June 2021 ATM. The project is underway with an estimated completion data of late 2022/ early 2023. Fifer's Field is not a large enough space. | Ms. Lazarow, a member of the Community Preservation Committee (CPC), explained that a preliminary application has been filed for one of several potential plans to put items at Liberty Field such as tennis or basketball courts, a walking court around the perimeter, and improved drainage on the soccer fields. The group will go back to PLACES to get better cost estimates for each item. Mr. Markiewicz, as liaison to the Recreation Commission, stated that he has been encouraging them to break down the plans into components, in order to look at doing some items before others. The group is actively engaged in this item.
|  |  |  | Action 4.3.1.3. Develop a consensus regarding the creation of bike and horse trails and create a plan for making these improvements where they are deemed appropriate. | Recreation Commission | Action 4.3.1.3- Ongoing, but concerns about meeting ADA requirements
|  |  |  | Action 4.3.1.4. Consider demand for, find appropriate locations for, and develop additional playing fields. | Recreation Commission | Action 4.3.1.4- There has been no new land available for additional playing fields. There has been no new land available for additional playing fields; however, we are actively looking at using exisitng softball fields that exist at Lincoln Properties and the Regency.
|  |  |  | Action 4.3.1.5. Improve and update the playground at Flerra Field. | Recreation Commission | Action 4.3.1.5- We added improvements to the playground at Flerra and installed a new fence around it.
|  |  | Strategy 4.3.2. Identify recreational needs, particularly for teens and seniors. | Action 4.3.2.1. Survey teens and seniors to determine specific needs. | Recreation Commission | Action 4.3.2.1- We plan to work more closely with the Council on Aging this year. In regards to teens, we helped to get funding for the Skate Park in Acton which is used by teens from Boxborough. We offered a yoga class for 5th and 6th graders at Blanchard, but there was not enough interest to get it started. | The COA Board received info briefings on proposed enhancements to Liberty Square Field. However, the board abstained from endorsing over concerns regarding cost vs. more pressing financial needs and challenges for seniors on fixed incomes to meet the Town's increasing taxes.
|  |  |  | Action 4.3.2.2. Coordinate with schools and Council on Aging to establish new recreational programs for teens and seniors. | Recreation Commission | Action 4.3.2.2- We have lots of ideas on programming, but the space to hold the programming is the limiting factor. Also, there is competition with AB Community Ed for programming and space (they can have access to Blanchard if we don't request it first). | Mr. Markiewicz explained that this item in ongoing. Due to the pandemic, the group is looking into other ways to support seniors.
| Aspiration 5. Is conscientious about consumption | Goal 5.1. Reduce the town’s overall carbon footprint. | Strategy 5.1.1. Actively explore options to adopt renewable energy generation sources for the town’s electricity needs. | Action 5.1.1.1. Collaborate with the Littleton Electric Light Department to expand its net metering program in order to allow continuation of solar installations, started by LittleBoxSolar, in the residential sector, and to create incentives for local businesses to install solar. | Sustainability Committee | • The SC has formally recommended the town have a solar bylaw and made specific recommendations about permitting. The Planning Board is considering the need for a town solar bylaw but has yet to formally address the issue. • No progress has been made with regard to developing an expanded net metering program to date. | Ms. Nolde, Chair of Sustainability Committe, explained that, when this program was started, LELD put a cap on how large a solar installation could be. Each size had a distribution chart and LELD regulated the size of the installation. No businesses were engaged in Town through LittleBoxSolar. LELD is in this action item in hopes of enlarging what they allow, in order to encourage more solar. LittleBoxSolar has been discontinued. There have been no discussions with LELD about expanding metering to incentivize solar in Town, but this is an ongoing action to be pursued.
|  |  |  | Action 5.1.1.2. Seek guidance from MAPC on Greening Boxborough, the town’s long-range sustainability plan. One area for follow up is to assess the feasibility of solar photovoltaic (PV) panels on municipal roofs. | Sustainability Committee | Status • Three separate energy related audits (LELD, Honeywell) have considered the suitability of PV panels on municipal roofs, parking lots and the former town landfill. These efforts concluded that the available options proved either too small or too old for viable installations. The single exception was the library with a large southerly facing roof. An opportune time to install panels on the library roof would be at the time the library is reroofed. | Ms. Nolde stated that the group is unclear about any document titled, “Greening Boxborough.” The Town has had three energy audits looking at the feasibility of putting PV panels on municipal roofs. The Library roof is the only one that would make sense. The Library roof is about 18 years old, and when it comes up for construction PV panel placement could be an option. The “Climate Action Plan” is the document being used in place of the “Greening Boxborough” document.
|  |  |  | Action 5.1.1.3. Negotiate with Littleton Electric Light Department to have them change their policy on net metering to allow more than bi-directional net metering. This would allow the town to develop a community-shared system for solar for use by residents and businesses in town. | Sustainability Committee | Status • The 5-megawatt solar project installed by Green Street Power in Boxborough in Jan. 2019 sells 100% of its electricity to LELD. LELD offers a subscription to Littleton and Boxborough customers interested in receiving a Renewable Energy Credit (currently $2.50 per month) that results from this power supply. | Ms. Nolde stated that there were negotiations between LELD, the Town, and an outside solar company, Green Street Power. This action item is hoping to encourage other ways to bring solar to the Town, particularly as a solar community. Nothing more can really be done until a Solar Bylaw is written. In response to a question from Ms. Markowitz, Ms. Nolde explained that there are many people in Town who cannot put solar panels on their roofs for various reasons. These people might be interested in buying into a community solar farm and have a share in it. Ms. Markowitz noted that the Planning Board is discussing a Solar Bylaw document. She requested any additional information from the Sustainability Committee that could be helpful to this document. Ms. Nolde explained that most of the money comes from RECs (Renewable Energy Credits). Residents need to ask for this credit.
|  |  | Strategy 5.1.2. Promote energy efficiency and conservation measures for all buildings in the municipal, residential, and commercial sectors. | Action 5.1.2.1. Collaborate with the Littleton Electric Light Department to create a communication strategy for available and expanded energy reduction incentive programs. | Sustainability Committee | Status • LELD Green Rewards Program is prominently advertised on their website, periodic newsletters and monthly bills. • LELD maintains a booth and promotes the Green Rewards program at Fifers Day and Harvest Day events. • The SC will invite LELD representative Connor Reardon to attend SC meetings at least once per quarter to improve communication and foster collaboration on achieving the goals of the 2030 Master Plan action items. • The SC will add a link to LELD Green Rewards program to the SC website. | Mr. Markiewicz noted that LELD’s latest newsletter did mention for residents to sign-up to receive the credit. Ms. Nolde explained that the solar farm on Mass Avenue adds to the renewable energy percentage that LELD has. Ms. Nolde stated that there is a list of items through the Green Rewards Program and that the Sustainability Committee would like for the LELD rep to come more often to their meetings.
|  |  |  | Action 5.1.2.2. Conduct outreach, awareness, and education programs for Boxborough’s residents and businesses regarding energy reduction strategies, and make this information available in an online resource library. | Sustainability Committee | Status • The BSC set up a Facebook page to increase interest and attract new members. Information is posted on the town website, the Boxborough Bee, Tax Bill inserts, Boxborough Neighbors, and Boxborough Next Door to advertise events, projects and ways to get involved. • The SC, with pro bono support from Emojot, has created the Boxborough Climate Change Survey scheduled for distribution to Boxborough residents and businesses in December 2020. The objective of the survey is to establish a baseline understanding of the town’s level of knowledge about climate change and to gauge their interest in additional information and guidance regarding climate change mitigation and related energy reduction strategies. • Based on the results of the survey, requested information will be made available in an online resource library. The SC will distribute a second survey to test the effectiveness of the education program and make adjustments as necessary. • The SC staffs an information booth at Fifers Day and Harvest Fair events each year with the notable exception of 2020 due event cancelations. • In October 2019, The SC Chair gave a 20-minute presentation to the Acton Boxborough Rotary Club to explain what the Sustainability Committee does, which was well received. • In 2019, Select Board approved the addition of two Alternates to the SC. The intent is to attract High School Students to become Interns to help with projects, especially to advocate for energy efficiency and sustainability. • SC members have become active in the Massachusetts Climate Action Network (MCAN) attending webinars and meetings. | Ms. Nolde explained that the group is on the cusp of doing an overall educational program for the Town. In the meantime, a Facebook page has been set up for community members and a variety of communication vehicles have been used to inform the Town. The group is ready to launch a survey regarding climate change, to gauge interest and knowledge levels in the Town about climate change mitigation. This is the first step in a two-step process. The group will then work to educate the public and return to see if the educational piece was effective. A talk was given in October 2019 to the Boxborough Rotary Club. Approval was received from the Select Board for two alternates for the Sustainability Committee. The hope is to get younger people and high school students involved. Barbara Salzman noted that there is a subgroup of the Massachusetts Climate Network that meets monthly. She attends to bring back information about what other communities in the area are doing. She is also the associate member serving on the HeatSmart Alliance to bring back information to Boxborough about what other towns are doing.
|  |  |  | Action 5.1.2.3. Encourage residents and businesses to reduce their energy consumption by 20%. Research and adopt means to measure reduction. | Sustainability Committee | Status • The SC placed a warrant article to adopt the Massachusetts Stretch Energy Building Code at May 2020 Town Meeting. The article was passed. | Ms. Nolde explained that this action item is one of the things the Town would need to do to be a Green Community. The group hopes that the Town can become a Green Community in the future. This would be designated under the Green Communities Act of 2008. If the Town is designated as such, it would receive $130,000 for the first year for energy projects. After that, the Town would show how it used the money and be able to apply for more funding based on other specific projects to possibly be awarded annual grants. Most of the surrounding towns are Green Communities.
|  |  |  | Action 5.1.2.4. Reduce municipal building energy consumption by 20%. Use existing database established by Energy Committee to measure reductions. | Sustainability Committee | Status • Three municipal facility energy audits have been conducted over recent years. The audits recommended installation of LED lighting, weather proofing windows and doors, adding insulation and other energy saving improvements. A follow up review needs to be done to determine what improvements have been made and what remain. • Utilizing DOER’s MassEnergyInsight (MEI) tool, the SC has established baseline and trend data on energy consumption at municipal buildings and facilities for many years. Municipal energy usage over the past three years (2016-2019) appears to be relatively stable. The Police Station and Library present the greatest potential opportunity for energy reduction. The SC will look carefully at the accuracy of the data and determine what options exist to reduce energy use at these two facilities in particular. LELD has offered to take over the inputting of data into the MEI database (previously done by a former SC member) and will produce annual reports for the Town.. • Net-Zero Energy Construction – The BSC recognized the careful work of architects and consultants, guided by Acton-Boxborough committees, to replace the Douglas and Gates schools with a highly efficient, net-zero energy building. BSC members attended a ABRSD Building Committee and contributed to the discussion and spoke in favor of building this school at Annual Town Meeting | Ms. Nolde explained that the last energy audit recommended that the Library, Town Hall and Police Buildings insulate, wrap pipes, and put LED lighting in. These are items that a Green Community would provide. There aren’t currently funds to complete these projects. Ms. Nolde explained that there is a MassEnergyInsight tool being used to measure energy consumption from municipal buildings, utilities, and fleet of vehicles each year. This gives the group a way to see if energy consumption is increasing or decreasing. This has been pretty stable over the past few years.
|  |  | Strategy 5.1.3. Develop mechanisms to support use of alternative fuel vehicles. | Action 5.1.3.1. Explore a plan for conversion of Town fleet to electric or hybrid vehicles. | Sustainability Committee | Status • 2 new police vehicles slated to purchased will be hybrid vehicles • As vehicles need to be replaced, each department is aware of the need to convert and will assess the feasibility of each purchase
|  |  |  | Action 5.1.3.2. Explore a plan for using alternative fuel vehicles for municipal vehicles. | Sustainability Committee | Status • Prior to any work in this area, the SC needs to assess the overall value of switching to alternative fuels that may continue to produce green house gas emissions.
|  |  |  | Action 5.1.3.3. Explore a plan for incentives to encourage new residential developments to install electric vehicle (EV) charging stations. | Sustainability Committee | Status • The SC believes that once a sufficient number of electric vehicles are in use, the charging stations will follow. | Explore grant opportunities for location on municipal properties. Suggest Sustainability Committee take the lead; Consider Solar Bylaw for 2021 ATM; Consideration of a tree bylaw for possible ATM 2021.
|  |  |  | Action 5.1.3.4. Explore a plan for incentives to encourage new and existing office developments to install electric vehicle charging stations. | Sustainability Committee | Status • The SC believes that once a sufficient number of electric vehicles are in use, the charging stations will follow.
|  |  | Strategy 5.1.4. Implement strategies for climate change resiliency and adaptation. | Action 5.1.4.1. Complete a climate change resiliency action plan. | Town Planner | The final report of the Municipal Vulnerability Preparedness program grant may be similar to what was sought by completing the climate change relisiency plan. The final report will be available in next few months, winter 2020/2021. | Status • In October, 2020 the BSB issued a Climate Change Statement that committed the board to take immediate, meaningful and ongoing actions to mitigate Climate Change and it’s affects on Boxborough residents and businesses. • The Boxborough Municipal Vulnerability Preparedness (MVP) planning workshop will be conducted on November 5, 2020. • SC is currently seeking funding to conduct a Carbon Emissions Inventory as a first step in developing a Climate Action Plan which will focus on prevention and mitigation through reducing green house gas emissions. | WRC members worked on the MAPC regional MAGIC Climate Change Resiliency Plan completed in 2017.
|  |  |  | Action 5.1.4.2. Implement climate change resiliency recommendations, including updating the Town’s Hazard Mitigation Plan. | Town Planner | The Town Planner submitted a Statement of Interest for Building Resilient Infrastructure Communities (BRIC) grant funding. If we apply and receive BRIC funding, it is anticipated that the total cost of the project to be about 20-25K, making the local share up to 5K. | Status • Possible MVP Action Grant and/or FEMA BRIC Grant
|  |  | Strategy 5.1.5. Pursue a Massachusetts Green Communities designation. | Action 5.1.5.1. Continue to pursue designation of Boxborough as a Green Community. | Sustainability Committee | Status • Presentation at recent (Oct. 2020) SC meeting by Kelly Brown, Regional Coordinator of the Green Community Division at DOER about the process and requirements to become a Green Community • Follow up communication between Kelly Brown and Town Planner regarding zoning requirements • Information meeting between Town Administrator, DOER and LELD to clarify eligibility issues | Mr. Ferrara, Town Administrator, explained that part of the Green Communities relies upon the State and making sure that the Town is eligible. The Town is trying to find out what the boundaries and restrictions are for this process.
| Aspiration 6.Is affordable and accessible | Goal 6.1. Increase the availability of housing in Boxborough, including subsidized, market rate, rental, and for sale homes. | Strategy 6.1.1. Continue current efforts to maintain and improve upon the availability of affordable homes. | Action 6.1.1.1. Monitor units on the Town’s Subsidized Housing Inventory to ensure compliance with affordability restrictions. | Housing Board | This is done on an ongoing basis with the support of Metro West Collaborative Development of the Assabet Regional Housing Consortium. This is also done through sending letters to members of the Town to make sure that affordable housing stock remains affordable.
|  |  |  | Action 6.1.1.2. Update the Boxborough Housing Production Plan as necessary. | Housing Board | Mr. Murphy stated that the Housing Production Plan probably does need to be updated to emphasize some of the items that have come to light recently. The existing plan that emphasizes rental housing is a good template. | Ms. Markowitz suggested that the group draft a supplement to update to where the Town is today, as it was originally drafted in 2015. Mr. Murphy stated that the group will take this on as an action item within a year. Mr. Fowlks questioned what is considered to be affordable housing. Mr. Murphy stated that the metrics are determined on the basis of HUD’s average incomes for the Boston/Metro area. These are quite high, which is why the numbers are what they are.
|  |  |  | Action 6.1.1.3. Support the development of rental housing through the Comprehensive Permit process. | Housing Board | The BHB was supportive of the development of Paddock Estates at Boxborough, which is Chapter-40B rental housing. No Chapter-40B developments, ownership or rental, have been proposed in the past several years, and we are not aware of any of that are in the offing. Developing rental affordable housing is one of the key recommendations of our Housing Production Plan, and we intend to support it, given the opportunity. | Mr. Les Fox added that, once the census is complete, it would be good for the group to go back and look at the SHI rolled into the 10% mandate. Then the group needs to look at what it can do to help people locally and supply what is really needed for housing. Ms. Markowitz noted that there has been some discussion about adding inclusionary zoning to the zoning ordinances. In reviewing data, approximately 40% of the housing stock in Town was at $500,000 or less. Mr. Mark White questioned what an affordable home is defined as, in order to know what types of housing is being encouraged in Town. Mr. Murphy stated that the group believes an affordable home to be about $400,000. There is a need for housing of this price point in Town. It is unclear how to achieve higher densities in Town. Ms. Markowitz explained that, out of the 350 single-family homes below $500,000 in Town, 288 of those are in the $400,000-450,000 range, and 46 are in the $300,000-400,000 range. The majority of the condos are between $100,000-200,000 range, and only a handful are in the $200,000- 300,000 range.
|  |  |  | Action 6.1.1.4. Identify strategies that would allow extremely-low income and very-low income households to access rental housing through tenant-based rental assistance programs. | Housing Board | We developed the Boxborough Rental Assistance Program (BRAP). The BRAP targets low income households, and currently assists up to twelve Boxborough households. We are presently evaluating ways in which the program can be expanded to help households that are adversely affected by COVID-19, climate change, and economic problems.The group is having trouble filling all 12 spots. There may be a need for temporary assistance. Or the group may look to supplement the purchase of air conditioners in order to help people through difficult times.
|  |  | Strategy 6.1.2. Support the development of a diverse mix of housing that meets the needs of Boxborough residents across all income and age groups. | Action 6.1.2.1. Identify ways to develop housing in Boxborough that is affordable to households with moderate incomes. | Housing Board | Boxborough’s biggest housing deficit appears to be mid-range housing. The Housing Board had hoped that mid-range housing could be developed on the Stow-Road property, but that proved very difficult. The Boxborough Building Committee is currently evaluating whether a Public Safety Facility can be placed on the property. The development of mid-range housing is complicated by the high cost of land in Boxborough. | In response to a question, Mr. Fowlks stated that he believes the group should look at what types of professions are needed in Boxborough and what types of housing are needed for that income range. In response to a question from Mr. Fox, Mr. Markiewicz stated that there is nothing in the zoning that wouldn’t allow prefabricated housing, but if that housing was stacked, there becomes an issue with multi-family housing. Ms. Markowitz explained that the Planning Board is looking at accessory dwelling unit bylaws. This may be a way to provide modest price housing in Town.
|  |  |  | Action 6.1.2.2. Develop a downpayment assistance program that could be used in conjunction with LIP/ Chapter 40B homeownership projects. | Housing Board | A down-payment assistance plan, often called “soft-second” program, uses a second, subordinate mortgage loan to cover down payment and closing costs. The payment schedule is deferred so that borrowers do not have to make any payments until/unless they sell their home or refinance their mortgage. The BHB regards this as a short-term, low-priority task, as described in Fig. 1 from our submission to the Master Plan Update Committee. Figure 1 places various tasks in a priority-time frame plane. As the figure indicates, we recommended that the task be eliminated. Somehow, that didn’t happen. There is nothing wrong with a down-payment assistance program. However, our Housing Production Plan recommends the production of more rental affordable housing. The assistance plan would help retain our existing ownership housing, but it probably would only be critical to units from the Condo Exchange Program, where the small (but growing) differences between the prices of affordable and market units diminish the attractiveness of the affordable units. We haven’t done anything on this task, but instead have been concentrating our energies on other more important tasks.
|  |  |  | Action 6.1.2.3. Prioritize seniors’ housing needs, such as accessibility features, in the permitting and development of all multi-family development projects. | Planning Board | Review 521 CMR (Architectural Access Board Rules and Regs) addresses accessibility requirements in Mass. to determine if bylaw can be modfied to include two-family units. Explore visit-ability and accessibility requirements such as ramps, stairs and curbcuts for multi-family units. Consider establishment of a town entity on senior needs to pursue grant monies to make housing more accessible. | A Habitat for Humanity home would be great for Boxborough. Aside from increasing the affordable housing in Boxborough, the BHB believes that such a project would have widespread benefits. We have not been able to find a suitable property. Ms. Markowitz stated that some research has been done on the 521 CMR. Mr. Mark Barbadoro stated that he called the MA Office on Disability and the Architectural Access Board to ask if any rules could be implemented through zoning to create enhanced requirements for accessibility for 1-2-bedroom homes, senior housing, etc. The response was to check with a lawyer and that it probably can’t be done. Ms. Markowitz also stated that there was the possibility of a private effort of committees to pursue grants moneys to make modifications to homes to make them more accessible.
|  |  |  | Action 6.1.2.4. Analyze the prevalence of “tear-downs” in Boxborough to determine if the demolition of existing single-family homes is contributing to the limited supply of homeownership opportunities for moderate-income households. | Planning Board | Number of tear downs do not seem to be signficant but check with Building Inspector. Demolition Delay bylaw in place allows Historical Commission to review. Pre-existing, non conforming lots require ZBA review. Allows for 100% size increase. Review other towns' bylaws on similar issue.
|  |  | Strategy 6.1.3. Proactively plan for Boxborough’s housing needs to improve the quality, design, and variety of available housing. | Action 6.1.3.1. Identify existing municipally owned parcels of land that are suitable sites for Local Initiative Program (LIP) affordable housing projects. | Housing Board | Mr. Murphy stated that there hasn’t been much of an opportunity for this item. This is ongoing.
|  |  |  | Action 6.1.3.2. Identify privately owned parcels of land that could be acquired by the Town for affordable housing development. | Housing Board | Mr. Murphy stated that the group has looked at several properties in Town for this action item, but none of them have yet worked out. This is ongoing.
|  |  | Strategy 6.1.4. Amend local policies and monitor regulatory compliance to reduce regulatory barriers and proactively plan for Boxborough’s housing needs. | Action 6.1.4.1. Review the Town’s Zoning Bylaw land use controls, including quadrangle requirements, to better understand how this requirement affects the development potential of oddly shaped, but otherwise suitable land parcels. | Planning Board | ZBA not seeing lots of requests. Dimensional Requirements Footnote #7. PB Does not wish to make Dimensional Requirements more restrictive. Mr. Barbadoro stated that he’s unsure of the benefit to the Town of opening up more oddly shaped lots to be built on.
|  |  |  | Action 6.1.4.2. Identify barriers to multi-family development, including use and intensity restrictions, in the Town’s Zoning Bylaw as a means to support more housing options in Boxborough. | Planning Board | Evaluate recommendations from Zoning Bylaw Audit (Nov 2020)- which suggests reconsider the restrictions on use (a special permit only in B1) and density (three units per acre). Ms. Markowitz stated that the Planning Board has discussed this briefly. The Zoning Diagnostic has been received, with a recommendation to consider restrictions on use and density. This is an ongoing conversation for the Planning Board.
|  |  |  | Action 6.1.4.3. Analyze the efficacy of accessory dwelling units, both attached and detached, as a means to meet affordable housing needs in Boxborough. Review the bylaw language, as well as units that have been constructed since the bylaw was enacted, to determine if amendments are necessary to expand its use. | Planning Board | Consider increased size beyond 600 sf in bylaw; requirements that must be owner, or relation of owner living in unit. Check Board of Health requiring separate systems for accessory unit. Study other Town ADU bylaws for non-owners (Concord, Acton) Review Lodging House License requirements.
|  |  | Strategy 6.1.5. Promote universal/ inclusive design for new construction and renovations to increase accessibility for all, including people with disabilities. | Action 6.1.5.1. Identify barriers to universal/ inclusive design in existing zoning bylaws and amend as necessary | Planning Board | Similar to 6.1.2.3 above, which suggests a review of 521 CMR (Architectural Access Board Rules and Regs) which addresses accessibility requirements in Mass. Suggest establish a town entity on senior needs to pursue grant monies to make housing more accessible. Ms. Markowitz stated that she doesn’t believe there are other barriers to this in the bylaws. Mr. Barbadoro stated that there are almost no accessibility requirements needed for 1 and 2 family dwellings. He questioned if the zoning wants to encourage multi-family dwellings, which would require accessibility requirements. One thing might cause another to be solved.
|  |  |  | Action 6.1.5.2. Improve recreational facilities beyond MassDOT and ADA guidelines, such as adding handicap accessible portable toilets at the Town’s recreational fields. | Recreation Commission | No update from the Recreation Commission at this time.
| Aspiration 7. Is regionally well-connected | Goal 7.1. Increase the quality, safety, accessibility, and reliability of transportation options for all income and age groups. | Strategy 7.1.1. Encourage active modes of transportation, such as walking and biking. | Action 7.1.1.1. Consider adoption of “Complete Streets” policy that would improve safe road access for all users, including bicyclists and pedestrians. | Planning Board | PB needs further discussion on sidewalks and roadway markings etc. Board will review Complete Streets Prioritization Plan in further detail. Ms. Markowitz stated that the Complete Streets Prioritization Plan has not yet been formally adopted by the Planning Board. The projects in this document would require funding from multiple sources.
|  |  |  | Action 7.1.1.2. Develop a prioritized plan for new sidewalks and bicycle infrastructure to connect to 1) schools, 2) recreational resources, 3) shopping/ dining, 4) Commuter Rail, and 5) residential areas. Include input from residents, businesses, and regional organizations in the plan. | Planning Board | Futher review and discussion per item above
|  |  |  | Action 7.1.1.3. Implement the 2003 Economic Development Trail Master Plan along Route 111/ Massachusetts Avenue. | Planning Board | Per Town Planner and Town Administator, Route 111, as state-owned highway needs to address drainage issues prior to or as part of any sidewalk project. High costs associated with drainage improvements. Municipal Vulnerability Project Core Group may seek Action Grants towards this. | Mr. Corson noted that something needs to be done to improve pedestrian travel, drainage and curbing for a sidewalk, along Route 111. This is a State road, and this may be a regional project or something from MASSDOT to pursue. Ms. Markowitz stated that the Mass Avenue sidewalk has taken a lot of funding and effort on behalf of the Town. Funds were not accepted for a sidewalk along Stow Road, so the Planning Board accepted a payment in lieu. The group is not looking to do a lot of sidewalk construction, other than what is underway.
|  |  |  | Action 7.1.1.4. Provide bicycle parking at destinations throughout town including but not limited to Town Hall, Fifer’s Field, Hayward Farm/ Oscar’s Burritos, Nashoba Valley Olympia, and additional capacity at Liberty Fields. | Recreation Commission | Action 7.1.1.4- Ongoing. The plans for Liberty will include more bike parking. Also, we will offer the building of bike racks as a community service opportunity to Eagle Scouts who are looking for a project. | Mr. Markiewicz explained that this is probably something the Recreation Commission will take up next year. This is an ongoing project. The energy is being focused right now on Liberty Fields.
|  |  | Strategy 7.1.2. Identify and promote solutions to improve local transportation options. | Action 7.1.2.1. Coordinate local transportation options to provide an on-demand shuttle that can serve commuters, reverse commuters, and local daytime trips. | Select Board | Mr. Fowlks stated that the COA shuttle is available. There has not been much action on this during COVID. | The COA continues to offer van services for seniors. In addition, COA has applied for ARPA funds to enhance transportation for senior attendance at medical appointments.
|  |  |  | Action 7.1.2.2. Explore new and innovative options to serve residents’ commuting needs, such as ride- or carsharing services. | Select Board | Mr. Fowlks questioned why the Town would try to work past a private business that would probably serve residents more readily. | The COA continues to offer van services for seniors. In addition, COA has applied for ARPA funds to enhance transportation for senior attendance at medical appointments.
|  | Goal 7.2. Continue to engage in partnerships with surrounding towns and the region. | Strategy 7.2.1. Continue participation in regional planning conversations and decision-making. | Action 7.2.1.1. Continue participation in MAPC (Metropolitan Area Planning Council) and MAGIC (Minuteman Advisory Group on Interlocal Coordination) subregional council meetings and initiatives. | Select Board | Mr. Fowlks stated that the Board has continued to participate in these meetings and that he is the current liaison to MAPC, as well as Ms. Markowitz. | PB Participates in monthly MAGIC meetings
|  |  |  | Action 7.2.1.2. Continue to advocate for regional transportation solutions with Regional Transportation Authorities (RTAs) and as a member of the Boston Region Metropolitan Planning Organization, CrossTown Connect Transportation Management Association, and 495/MetroWest Partnership, and with other regional entities and neighboring towns. | Select Board | Mr. Fowlks stated that the Board has continued to advocate for transportation solutions with these other groups. Mr. Fowlks stated that the Board has continued to push back on carbon emissions taxis because thereare no alternatives to commuting. The group has asked for better public transport options to Boston. This is ongoing. Mr. Fox stated that the CrossTown Connect item did not work well and participation was declining. He questioned if it should be removed from the list. Mr. Fowlks stated that it should probably be removed, but that it should be tabled for now. Ms. Markowitz asked how many Uber and Lyft rides occur in Town. Mr. Ferrara stated that he would look into this item. Ms. Markowitz stated that there might be some interest in getting access out from the CISCO campus to the Littleton/Acton train station.
|  | Goal 7.3. Pursue regional approaches for open space and recreation. | Strategy 7.3.1. Explore opportunities to improve open space and recreation opportunities across municipal borders with neighboring communities. | Action 7.3.1.1. Identify recreational services and facilities in Boxborough and neighboring towns and plan for sharing of these facilities where feasible and desirable. | Recreation Commission | Action 7.3.1.1- We helped Acton with funding for the building of the Skate Park. We have reached out to other towns, but they all have more extensive recreational programming, facilities and staff and have no need to partner with Boxborough. | Mr. Markiewicz stated that he doesn’t believe any actions have been taken on this yet, but it is ongoing.
|  |  |  | Action 7.3.1.2. Coordinate with neighboring communities to develop a regional open space and trail network. | Town Planner | Mr. Corson stated that there is no update on this item at this time. He will look into partnering with the Land Stewards for a future update. Ms. Markowitz stated that a bike/hike along communities with stops along the way, might be something for the Recreation Commission to pursue.